## Sheet1
Risk # | The Risk of/That | Likelihood Score | Impact Score
R1 | A cybersecurity breach | 4 | 2
R2 | Operational downtime | 2 | 2
R3 | Workforce resistance to new systems | 6 | 8
R4 | Data privacy non-compliance | 1 | 9
R5 | Reputational loss | 3 | 8
R6 | System integration failure | 7 | 7
R7 | Inventory mismanagement due to automation errors | 3 | 7
R8 | Supplier failure to meet ESG standards | 3 | 9
R9 | Overreliance on few tech vendors | 1 | 9
R10 | Failure in AI-based demand forecasting | 7 | 8
R11 | Negative public perception of automation impact on jobs | 6 | 1
R12 | Data synchronization issues between stores and distribution centers | 1 | 6
R13 | Ineffective last-mile delivery innovation | 1 | 1
R14 | Cyber attack on autonomous vehicle fleet | 8 | 9
R15 | IoT sensor malfunction in warehouses | 3 | 7
R16 | Regulatory pushback on drone deliveries | 6 | 6
R17 | Delays in warehouse construction | 6 | 6
R18 | Labor shortage in robotics support roles | 5 | 4
R19 | Poor training on new digital tools | 5 | 7
R20 | Software bugs in order fulfillment algorithms | 3 | 6
R21 | AI bias in predictive analytics | 8 | 7
R22 | Overestimation of market demand due to flawed data | 6 | 9
R23 | Logistics delays during peak seasons | 6 | 9
R24 | Increased emissions due to supply chain redesign missteps | 6 | 7
R25 | Third-party data vendor reliability issues | 2 | 3
R26 | Non-compliance with cross-border digital trade regulations | 2 | 6
R27 | Malfunctioning temperature control for perishable items | 6 | 8
R28 | Warehouse worker injuries from automated machinery | 3 | 1

## RiskRegister
| Likelyhood/Impact | 1 | 2 | 3 | 4 | 6 | 7 | 8 | 9
| 1 | 1: 1; 6: 1; 9: 2
| 2 | 1: 0; 2: 1; 3: 1; 6: 1
| 3 | 1 |  |  |  | 1 | 2 | 1 | 1
4 | bar: 1 to 9
5 | bar: 1 to 9
| 6 | 1 |  |  |  | 2 | 1 | 2 | 2
7 | bar: 1 to 9
8 | bar: 1 to 9
| Likelyhood/Impact | 1: Low Impact; 2: Moderate Impact; 3: High Impact
Total risk score | Unlikely | 1: Low Risk (4)
| Likely | 2: Moderate Risk (5)
| Highly likely | 3: High Risk (19)

## Heatmap
| High | 9 | R13 |  | R28 |  |  | R11
|  | 8 |  | R2 |  | R1
|  | 7 |  | R25
| Moderate | 6 |  |  |  |  | R18
|  | 4 | R12 | R26 | R20 |  |  | R16, R17
IMPACT | Low | 3 |  |  | R7,R15 |  | R10 | R24 | R6 | R21
|  | 2 |  |  | R5 |  |  | R3, R27 | R10
|  | 1 | R4, R9 |  | R8 |  |  | R22, R23 |  | R14
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
|  |  | Low |  |  | Moderate |  | High
LIKELIHOOD